## Sheet1
Bug ID	Component	Status	Summary
124922	kernel	NEEDINFO	[Limit-Test] Unable to boot Host with over 8TB Memory defined
125709	libvirt	NEEDINFO	Migration of a busy guest via p2p-tunnelled was hanging and "paused" VM on target host disappeared.
132355	KVM	NEEDINFO	KVM guest became unresponsive after displaying kernel BUG message on console session
130061	libvirt	NEEDINFO	[zKVM GTP1503] Unable to virsh start a KVM guest from the disk which was created by a iscsi target defining ECKD device as backstore
131312	kernel	NEEDINFO	Change kernel config parameter TUN_READQ_SIZE to 2500
126650	OpenStac	DEFERRED	iothreads with ICM
132389	HVM	REOPENED	Need additional package (python-magic) to support Ginger
126365	kernel	ASSIGNED	Default Network Performance is less than half of line speed
133395	Installe	ASSIGNED	installer kdump is not enabled for 8GB dump size
131888	BaseOS	ASSIGNED	Change SCLP_TYPE and SCLP_SYSLEVEL to identifier KVM for IBM z Systems
133802	Installe	ASSIGNED	Installer doesn't show error messages. Using kickstart
133919	Installe	ASSIGNED	installer kdump upper limit in Size scope not working for dump
131448	Document	ASSIGNED	Openvswitch GRE tunnel to vulcan host not working (from other host)
131898	BaseOS	ASSIGNED	GDB does not display the vector registers when info all-registers command is issued
126976	Unknown	ASSIGNED	Corrupted ftp server repository when ISO9660 Joliet extension is used
129117	BaseOS	ASSIGNED	[zKVM GTP1503] ISCSI initiator can write to the write-protected ECKD device
132438	libvirt	ASSIGNED	Soltest: Vulcan Beta3.3: internal error: Device alias was not set for scsi controller with index 0
132672	network	ASSIGNED	Network throughput is reduced by ~20% when nf_conntrack_ipv4 nf_defrag_ipv4 modules are loaded
132461	BaseOS	ASSIGNED	after zipl and reboot, the number of cpus reported by lscpu and cat /proc/cpuinfo on the host differs from maxcpus= value in /etc/zipl.conf
126364	network	ASSIGNED	uperf throughput on Kronos beta3.6 and beta6.6 degrades as nprocs increased from 50 to 250
131393	network	ASSIGNED	Unable to ssh into host with multiple network interfaces
125768	libvirt	ASSIGNED	VIrsh shutdown gets journal message: “nl_recv returned with error: No buffer space available”
132475	QEMU	ASSIGNED	fio random read test (8K, 1 job) regresses ~5% from beta2.3 to beta3.2
133711	kernel	ASSIGNED	Storage key optimization request for Vulcan
133852	kernel	ASSIGNED	uperf 30K stream tests performance regresses ~8% in Vulcan beta3.5
132012	libvirt	ASSIGNED	managedsave of 15 guests in parallel, one hangs
132559	Build	ASSIGNED	Move post changes of /etc/sysctl.conf to rpm package
133478	Installe	ASSIGNED	exported VG makes installer fail with KVMIBMCO03013
133400	Installe	ASSIGNED	installer allows to start installation on a system having not enough memory
132203	Document	ASSIGNED	default libvirtd network virbr0 is enabled after installation, but not documented
132737	Build	ASSIGNED	Move disable of sendmail.service in post changes to rpm
133401	QEMU	ASSIGNED	using watchdog-action=none nothing happens, after the watchdog bites, I cannot execute the watchdog-test code anymore, until I end the watchdog and restart it
133687	Installe	ASSIGNED	ksvalidator fails on 'kdump' keyword
127205	QEMU	ASSIGNED	BEAM: Passing untrusted input to strcpy/strcat
133359	libvirt	ASSIGNED	Switching CPUs leads to error message - nl_recv returned with error: No buffer space available
133047	HPM	ASSIGNED	Improve warning message on insecure CLI commands
125443	BaseOS	ASSIGNED	Message repeatedly logged - Failed to reset devices.list on /machine.slice: Invalid argument - after starting a guest
128901	Installe	ASSIGNED	[R-Test] "Pane is dead" when FTP server is interrupted
133917	kernel	OPEN	[JPT 645802] zKVM SCSI IPL fails with LPAR dump when image has 6TB of storage or greater on z13
133422	HPM	OPEN	zHPM restarted with many request failure message