## Sheet1
Bug ID	Component	Status	Summary
139959	BaseOS	FIXEDAWAITINGTEST	Genearation of debugreport failing on ubuntu kernel.
139994	s390-Tools	NEEDINFO	zgetdump returns "No valid dump found" on SCSI dump device
141352	Libvirt	FIXEDAWAITINGTEST	Unable to open file: /var/log/libvirt/qemu/zs93k1g99157.log: Too many open files.
141880	Libvirt	TESTED	Unable to start Ubuntu guests with memballoon default.
142402	Network	OPEN	uperf TCP_RR test regresses ~15% from alpha2.1 to beta1.2
142241	Unknown	OPEN	ld test suite fails for Zeus
141957	Build	OPEN	Is systemtap 3.0-2 needed for Zeus ?
140690	BaseOS	ASSIGNED	kdump broken with kernel 4.4
139731	Build	ASSIGNED	Fedora kernel spec file requires higher linux-firmware and xfsprogs package versions as we have in Metis
141060	kernel	ASSIGNED	sysbench oltp mysql scale up test regresses 40% from metis beta3.2 to zeus alpha 2.1
140186	BaseOS	ASSIGNED	Stopping firewalld causes openvswitch kernel modules to be unloaded
132559	Build	ASSIGNED	Move post changes of /etc/sysctl.conf to rpm package
141360	QEMU	FIXEDAWAITINGTEST	Guests hang when attempting to reboot on Vulcan FP1
140831	kernel	DEFERRED	kernel module signing is not implemented
140626	BaseOS	NEEDINFO	NetworkManager user process faults when running openvswitch regression tests
141276	Unknown	NEEDINFO	logrotate failing to run due to wok misconfiguration
140387	BaseOS	NEEDINFO	makedumpfile --eppic fails with Zeus