## Raw-Data
				All	Total Open
Week	Date	Open (Blocked/Ship Issue)	Open (Other)	Need Info	Assigned / ReOpened	FAT	Rejected / Closed			New Defects	Closed Defects		Block	Ship Issue	High	Nomal	Low	Predicted Open
	11/16	0	3	8	54	6	179	255	71	12	20	-8				71		71
	11/23	0	4	5	41	21	192	268	71	13	13	0				71		68
	11/30	0	3	5	44	14	203	273	68	5	11	-6				68		65
	12/07	0	2	5	31	21	206	279	61	6	3	3	0	1	16	40	4	62
	12/14	0	2	6	37	8	237	292	53	13	31	-18	1	1	15	32	4
	12/21	0	8	7	41	8	243	308	64	16	6	10	1	3	19	35	6
	12/28	0	1	8	38	11	248	312	59	4	5	-1	0	5	17	33	4
	01/04	0	0	8	41	9	255	313	58	1	7	-6	0	4	17	33	4
	01/11	0	2	2	43	6	266	319	53	6	11	-5	1	3	14	31	4
	01/18	0	5	2	34	10	282	333	51	14	16	-2	1	4	14	29	3
	01/25	0	3	2	24	15	291	340	44	7	9	-2	0	2	13	26	3
	02/01	0	9	4	15	10	309	360	38	20	18	2	0	2	9	22	5
	02/15	0	6	6	47	1	323	383	60	23	14	9	0	2	20	32	6
	02/22	0	6	4	42	9	330	392	61	9	7	2	0	4	16	35	6
	02/29	1	6	5	33	5	345	396	50	4	15	-11	0	4	13	29	4	36
	03/07	0	7	6	22	3	366	405	38	9	21	-12	0	1	15	20	2	32
	03/14	1	4	5	16	2	380	409	28	4	14	-10	0	1	12	15	0	28
	03/21					22

Week	Date	Open (Blocked/Ship Issue)	Open (Other)	Need Info	Assigned / ReOpened	FAT	Rejected / Closed
1	09/28	2	4	13	36	0	109	165	56
2	10/12	8	9	11	36	10	116	187	75	22	7	15
3	10/19	1	7	10	47	1	130	197	67	10	14	-4
4	10/27	2	11	13	38	9	140	214	74	17	10	7
5	11/02	0	6	10	59	2	155	234	77	20	15	5
6	11/09	0	0	8	50	21	159	243	84	9	4	5				84
7	11/16	0	3	8	54	6	179	255	71	12	20	-8				71
8	11/23	0	4	5	41	21	192	268	71	13	13	0				71
9	11/30	0	3	5	44	14	203	273	68	5	11	-6				68
10	12/07	0	2	5	31	21	206	279	61	6	3	3	0	1	16	40	4
11	12/14	0	2	6	37	8	237	292	53	13	31	-18	1	1	15	32	4
12	12/21	0	8	7	41	8	243	308	64	16	6	10	1	3	19	35	6
13	12/28	0	1	8	38	11	248	312	59	4	5	-1	0	5	17	33	4	50
14	01/04	0	0	8	41	9	255	313	58	1	7	-6	0	4	17	33	4	42
15	01/11	0	2	2	43	6	266	319	53	6	11	-5	1	3	14	31	4	36
16	01/18	0	5	2	34	10	282	333	51	14	16	-2	1	4	14	29	3	30
17	01/25	0	3	2	24	15	291	340	44	7	9	-2	0	2	13	26	3	24
18	02/01 / Open Defect by Severity (weekly)	0	9	4	15	10	309 / New and Closed defects (weekly)	360	38	20	18	2	0	2	9	22	5	22
19	02/16	0	6	6	47	1	323	383	60	23	14	9	0	2	20	32	6	20

				All Defects

## Sheet2
Month	Current	Jan	Feb	March	April
Resolution
Fix by IBM	170	122	124	141	170
Not a Bug	70	53	53	60	70
Will not fixed	21	20	20	20	21
Documented	9	9	8	8	9
Duplicates	16	9	10	12	16
Unreproducable	9	7	7	8	9
Fix already available	4	2	3	3	4
Fix by Community	2	2	2	2	2
Alternate solution available	2	2	2	2	2
Fix by Distro	2	2	2	2	2
Total	305	228	231	258	305

	231 Closed Defects

## Sheet3
Bug ID	Ship-Issue Defects	Status	Reporter
118395	Default Network Performance is less than half of line speed	OPEN	mksully@us.ibm.com
118397	uperf throughput on Kronos beta3.6 degrades as nprocs increased from 50 to 250	OPEN	mksully@us.ibm.com
119898	network throughput between two lpars is about half expected level when both lpars are using the same OSA Ethernet device	OPEN	mksully@us.ibm.com
120739	Openstack Kilo requires dnsmasq paket to be at least on version 2.67	ASSIGNED	NIKLAUS@de.ibm.com