## Raw-Data
				All	Total Open
Week	Date	Open (Blocked/Ship Issue)	Open (Other)	Need Info	Assigned / ReOpened	FAT	Rejected / Closed			New Defects	Closed Defects		Block	Ship Issue	High	Nomal	Low	All Open
	11/16	0	3	8	54	6	179	255	71	12	20	-8				71		71
	11/23	0	4	5	41	21	192	268	71	13	13	0				71		68
	11/30	0	3	5	44	14	203	273	68	5	11	-6				68		65
	12/07	0	2	5	31	21	206	279	61	6	3	3	0	1	16	40	4	62
	12/14	0	2	6	37	8	237	292	53	13	31	-18	1	1	15	32	4	59
	12/21	0	8	7	41	8	243	308	64	16	6	10	1	3	19	35	6	56
	12/28	0	1	8	38	11	248	312	59	4	5	-1	0	5	17	33	4	50
	01/04	0	0	8	41	9	255	313	58	1	7	-6	0	4	17	33	4	42
	01/11	0	2	2	43	6	266	319	53	6	11	-5	1	3	14	31	4	36
	01/18	0	5	2	34	10	282	333	51	14	16	-2	1	4	14	29	3	30
	01/25	0	3	2	24	15	291	340	44	7	9	-2	0	2	13	26	3	24
	02/01					22
	02/08					20
	02/15					18

Week	Date	Open (Blocked/Ship Issue)	Open (Other)	Need Info	Assigned / ReOpened	FAT	Rejected / Closed
1	09/28	2	4	13	36	0	109	165	56
2	10/12	8	9	11	36	10	116	187	75	22	7	15
3	10/19	1	7	10	47	1	130	197	67	10	14	-4
4	10/27	2	11	13	38	9	140	214	74	17	10	7
5	11/02	0	6	10	59	2	155	234	77	20	15	5
6	11/09	0	0	8	50	21	159	243	84	9	4	5				84
7	11/16	0	3	8	54	6	179	255	71	12	20	-8				71
8	11/23	0	4	5	41	21	192	268 / All Defects	71	13	13	0				71
9 / Open Defect by Severity (weekly)	11/30	0	3	5	44	14	203	273	68	5	11	-6				68
10	12/07	0	2	5	31	21	206	279	61	6	3	3	0	1	16	40	4
11	12/14	0	2	6	37	8	237	292	53	13	31	-18	1	1	15	32	4
12	12/21	0	8	7	41	8	243	308	64	16	6	10	1	3	19	35	6

				New and Closed defects (weekly)

## Sheet2
Month	Current	Jan	Feb	March	April
Resolution
Fix by IBM	170	122	124	141	170
Not a Bug	70	53	53	60	70
Will not fixed	21	20	20	20	21
Documented	9	9	8	8	9
Duplicates	16	9	10	12	16
Unreproducable	9	7	7	8	9
Fix already available	4	2	3	3	4
Fix by Community	2	2	2	2	2
Alternate solution available	2	2	2	2	2
Fix by Distro	2	2	2	2	2
Total	305	228	231	258	305

	231 Closed Defects

## Sheet3
Bug ID	Ship-Issue Defects	Status	Reporter
118395	Default Network Performance is less than half of line speed	OPEN	mksully@us.ibm.com
118397	uperf throughput on Kronos beta3.6 degrades as nprocs increased from 50 to 250	OPEN	mksully@us.ibm.com
119898	network throughput between two lpars is about half expected level when both lpars are using the same OSA Ethernet device	OPEN	mksully@us.ibm.com
120739	Openstack Kilo requires dnsmasq paket to be at least on version 2.67	ASSIGNED	NIKLAUS@de.ibm.com